## Defect Tracking Log
Cycle-1 DEFECT TRACKING LOG
Project Name | EWHEELZ APPLICATION
Program Manager | Sushmita Haldar
Project Manager | Sumeet Dhillon
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Test Case Id | Module | UI name | Defect Description | defect status | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
1 | 2023-03-21 | Sumeet | TC_UREG_001 | Travel | User registration | Registration page not available | Blocked | Executing/Controlling | Testing | Medium | tester | 2023-03-21 | 3 days | New | Add user registration or change Business Requirement |  |  | Not developed in 1st release | New
2 | 2023-03-21 | Sumeet | TC_AREG_001 | Admin | Admin registration | Registration page not available | Blocked | Executing/Controlling | Testing | High | tester | 2023-03-21 | 3 days | New | Add Admin reistration page |  |  | Not developed in 1st release |  |  |  | Post-Deployment
3 | 2023-03-21 | Sumeet | TC_ULOG_001 | Travel | User Log In | Does not ask for any user login credentials | Fail | Executing/Controlling | Testing | Medium | tester | 2023-03-21 | 3 days | New | Varify user with id ,pw or change Business Requirement |  |  | Not developed in 1st release
4 | 2023-03-21 | Sumeet | TC_ULOG_002 | Travel | User Log In | Users can login without User Id, password | Blocked | Executing/Controlling | Testing | Medium | tester | 2023-03-22 | 4 days | New | add Id, Pw or chane B.R. |  |  | Not developed in 1st release
5 | 2023-03-21 | Sumeet | TC_ULOG_007 | Travel | User Log out | No log out button available for general user | Blocked | Executing/Controlling | Testing | Low | tester | 2023-03-21 | 3 days | New | add logout foruser or change B.R. |  |  | Not developed in 1st release
6 | 2023-03-22 | Sumeet | TC_ALOG_001 | Admin | Admin Log In | Admin Id, password can not be submitted (button not working) | Fail | Executing/Controlling | Testing | High | tester | 2023-03-22 | 3 days | New | add an active Submit button |  |  | Not developed in 1st release
7 | 2023-03-24 | Anugha | BTTC_004 | Reservation | Book Ticket | Journey Date field does not work or does not take any input date | Fail | Executing/Controlling | Testing | Low | tester |  |  | New |  |  |  | poor coding
8 | 2023-03-24 | Anugha | BTTC_0010 | Reservation | Book Ticket | Check Availability button does not work | Fail | Executing/Controlling | Testing | High | tester |  |  | New |  |  |  | poor coding
9 | 2023-03-24 | Anugha | BTTS_0015 | Reservation | Book Ticket | User cannot enter Bank details | Fail | Executing/Controlling | Testing | Low | tester |  |  | New |  |  |  | poor coding
10 | 2023-03-24 | Anugha | BTTS_0017 | Reservation | Book Ticket | User cannot enter Card details | Fail | Executing/Controlling | Testing | Medium | tester |  |  | New |  |  |  | poor coding
11 | 2023-03-24 | Anugha | BTTS_0021 | Reservation | Book Ticket | User cannot enter NetAmount details | Fail | Executing/Controlling | Testing | Low | tester |  |  | New |  |  |  | poor coding
12 | 2023-03-24 | Anugha | BTTS_0025 | Reservation | Book Ticket | Cannot save the payment info | Fail | Executing/Controlling | Testing | High | tester |  |  | New |  |  |  | poor coding
13 | 2023-03-24 | Anugha | CTTS_001 | Reservation | Cancel Ticket | System shows error message- "No tickets found.Please provide valid Ticket Id" for any valid or invalid ticket Id entered | Fail | Executing/Controlling | Testing | Low | tester |  |  | New |  |  |  | poor coding
14 | 2023-03-22 | Libin | RMTC_012 | Route | Add Route | Travel Id can not be entered or validated | Fail | Executing/Controlling | Testing | High | tester | 2023-03-22 | 2 days | New | Dropdown button should be in working condition. |  |  | poor coding
15 | 2023-03-22 | Libin | RMTC_013 | Route | Add Route | Bus Ids are not retrieved from database | Fail | Executing/Controlling | Testing | High | tester | 2023-03-22 | 2 days | New | Dropdown button should be in working condition. |  |  | poor coding
16 | 2023-03-22 | Libin | RMTC_013 | Route | Add Route | Bus Id can not be entered manually | Fail | Executing/Controlling | Testing | High | tester | 2023-03-22 | 2 days | New | Option to add ID manually |  |  | poor coding
17 | 2023-03-22 | Libin | RMTC_014 | Route | Add Route | Journey Date field does not work or does not take any input date | Fail | Executing/Controlling | Testing | High | tester | 2023-03-22 | 2 days | New | The calendar function shold be working |  |  | poor coding
18 | 2023-03-22 | Libin | RMTC_015 | Route | Add Route | Arrival* fields takes any invalid input | Fail | Executing/Controlling | Testing | Medium | tester | 2023-03-22 | 2 days | New | Proper constraints should be there |  |  | poor coding
19 | 2023-03-22 | Libin | RMTC_17 | Route | Add Route | Fare* fields takes any invalid input | Fail | Executing/Controlling | Testing | Medium | tester | 2023-03-22 | 2 days | New | Proper constraints should be there |  |  | poor coding
20 | 2023-03-22 | Libin | RMTC_015 | Route | Add Route | Departure* fields takes any invalid input | Fail | Executing/Controlling | Testing | Medium | tester | 2023-03-22 | 2 days | New | Proper constraints should be there |  |  | poor coding
21 | 2023-03-22 | Libin | RMTC_016 | Route | Add Route | Submit button does not work | Fail | Executing/Controlling | Testing | High | tester | 2023-03-22 | 2 days | New | Submit button will work all data is inputted |  |  | poor coding
22 | 2023-03-22 | Shikha | TC_002 | Testimonial | Give Testimonial | System accepts Invalid Email Id. | Fail | Executing/Controlling | Testing | Medium | tester | 2023-03-22 | 2 days | New | Error Message showing "Your Feedback is not submitted as Invalid Email Id has been entered". |  |  | poor coding without data validation
23 | 2023-03-23 | Puneet | TC_001_AddUser TC_002_AddUser TC_003_AddUser TC_004_AddUser TC_005_AddUser TC_006_AddUser TC_007_AddUser TC_008_AddUser TC_009_AddUser TC_010_AddUser TC_011_AddUser TC_012_AddUser TC_013_AddUser TC_014_AddUser | Admin | Add User | Add user function is not available | Blocked | Executing/Controlling | Testing | High | Developer | 2023-03-23 |  | New | Implementing the Add user option into the admin page of the application |  |  | Not developed in 1st release
24 | 2023-03-23 | Puneet | TC_015_ViewUser | Admin | View User | View user function is not available | Blocked | Executing/Controlling | Testing | High | Developer | 2023-03-23 |  | New | Implementing the View user option into the admin page of the application |  |  | Not developed in 1st release
25 | 2023-03-23 | Puneet | TC_016_DeleteUser TC_017_DeleteUser TC_018_DeleteUser TC_019_DeleteUser TC_020_DeleteUser TC_021_DeleteUser | Admin | Delete User | Delete user function is not available | Blocked | Executing/Controlling | Testing | High | Developer | 2023-03-23 |  | New | Implementing the Delete user option into the admin page of the application |  |  | Not developed in 1st release
26 | 2023-03-23 | Puneet | TC_022_ChangePswd TC_023_ChangePswd TC_024_ChangePswd TC_025_ChangePswd TC_026_ChangePswd TC_027_ChangePswd TC_028_ChangePswd TC_029_ChangePswd TC_030_ChangePswd TC_031_ChangePswd TC_032_ChangePswd TC_033_ChangePswd TC_034_ChangePswd TC_035_ChangePswd TC_036_ChangePswd TC_037_ChangePswd TC_038_ChangePswd TC_039_ChangePswd TC_040_ChangePswd | Admin | Change Password | Change password function is not available | Blocked | Executing/Controlling | Testing | High | Developer | 2023-03-23 |  | New | Implementing the change password option into the admin page of the application |  |  | Not developed in 1st release
27 | 26-03-2023 | Sameep | TC_ADD_005 | Admin | Add Travel | Travel is added even though the Travel name field is empty | Fail | Executing/Controlling | Testing | High | Tester | 26-03-2023 | 2 days |  | It should display an error and not submit since it is a mandatory field |  |  | Data validaion not implemented
28 | 26-03-2023 | Sameep | TC_ADD_006 | Admin | Add Travel | Travel is added with the name with special characters | Fail | Executing/Controlling | Testing | High | Tester | 26-03-2023 | 4 days |  | It should display an error and not submit since it contains invalid name and values |  |  | Data validaion not implemented
29 | 26-03-2023 | Sameep | TC_ADD_009 | Admin | Add Travel | Travel is added with a default location option. | Fail | Executing/Controlling | Testing | High | Tester | 26-03-2023 | 3 days |  | It should display an error and not submit since no options were selected |  |  | Data validaion not implemented
30 | 26-03-2023 | Sameep | TC_ADD_014 | Admin | Add Travel | Travel is added even though the Travel address field is empty | Fail | Executing/Controlling | Testing | High | Tester | 26-03-2023 | 2 days |  | It should display an error and not submit since it is a mandatory field |  |  | Data validaion not implemented
31 | 26-03-2023 | Sameep | TC_ADD_015 | Admin | Add Travel | Travel is added with the address with special characters | Fail | Executing/Controlling | Testing | High | Tester | 26-03-2023 | 4 days |  | It should display an error and not submit since it contains invalid name and values |  |  | Data validaion not implemented
32 | 26-03-2023 | Sameep | TC_ADD_020 | Admin | Add Travel | Travel is added even though the Travel address field is empty | Fail | Executing/Controlling | Testing | High | Tester | 26-03-2023 | 2 days |  | It should display an error and not submit since it is a mandatory field |  |  | Data validaion not implemented
33 | 26-03-2023 | Sameep | TC_ADD_021 | Admin | Add Travel | Travel is added with the address with special characters | Fail | Executing/Controlling | Testing | High | Tester | 26-03-2023 | 4 days |  | It should display an error and not submit since it contains invalid name and values |  |  | Data validaion not implemented
34 | 26-03-2023 | Sameep | TC_ADD_025 | Admin | Add Travel | Travel is added even though the Travel address field is empty | Fail | Executing/Controlling | Testing | High | Tester | 26-03-2023 | 2 days |  | It should display an error and not submit since it is a mandatory field |  |  | Data validaion not implemented
35 | 27-03-2023 | Sameep | TC_ADD_026 | Admin | Add Travel | Travel is added with the address with alpha numeric characters | Fail | Executing/Controlling | Testing | High | Tester | 27-03-2023 | 4 days |  | It should display an error and not submit since it contains invalid name and values |  |  | Data validaion not implemented
36 | 27-03-2023 | Sameep | TC_ADD_027 | Admin | Add Travel | Travel is added with the address with special characters | Fail | Executing/Controlling | Testing | High | Tester | 27-03-2023 | 4 days |  | It should display an error and not submit since it contains invalid name and values |  |  | Data validaion not implemented
37 | 27-03-2023 | Sameep |  | Admin | Add Travel | User cannot add more than 10 records, it displays a Null Pointer Exception | Fail | Executing/Controlling | Testing | Major | Tester | 27-03-2023 | 10 days |  | It should add the record and display a successful message |  |  | Database query error
38 | 27-03-2023 | Sameep | TC_DEL_007 | Admin | Delete Travel | 1010 - The travel details are not visible, since the button does not function | Fail | Executing/Controlling | Testing | High | Tester | 27-03-2023 | 6 days |  | It should display details of the selected option. |  |  | Data validaion not implemented
39 | 28-03-2023 | Sameep | TC_VIEW_008 | Admin | View Travel | Bus details are added with a default option. | Fail | Executing/Controlling | Testing | High | Tester | 28-03-2023 | 3 days |  | It should display an error and not submit since no options were selected |  |  | Data validaion not implemented
40 | 28-03-2023 | Sameep | TC_VIEW_013 | Admin | View Travel | Bus details are added even though the fields are empty | Fail | Executing/Controlling | Testing | High | Tester | 28-03-2023 | 4 days |  | It should display an error and not submit since it is a mandatory field |  |  | Data validaion not implemented
41 | 28-03-2023 | Sameep | TC_VIEW_014 | Admin | View Travel | Bus details are added with the bus number with special characters | Fail | Executing/Controlling | Testing | High | Tester | 28-03-2023 | 4 days |  | It should display an error and not submit since it contains invalid name and values |  |  | Data validaion not implemented
Note on I10: ====== ID#AAAAW3lbf68 Julie Arnold (2022-04-07 05:00:46) Choose from the drop down box.
Note on J10: ====== ID#AAAAW3lbf7I John Casey (2022-04-07 05:00:46) Choose from the drop down box.
Note on K10: ====== ID#AAAAW3lbf7E Julie Arnold (2022-04-07 05:00:46) Choose from the drop down list
Note on O10: ====== ID#AAAAW3lbf7A Julie Arnold (2022-04-07 05:00:46) Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).