## Summary
| Overall progress of the QA cycle(Ontime, delayed, Stopped) | On time
| Total number of test cases | 150
| Number of testers | 6
| Test cycle duration | 4 days
Status for 03/21/2023
| Number of test cases planned | 37
| Number of test cases executed | 17
| Number of test cases executed overall | 17
| Number of defects encountered today | 15
| Number of defect encountered so far | 15
| Number of critical defects- still open | 10
Status for 03/22/2023
| Number of test cases planned | 38
| Number of test cases executed | 17
| Number of test cases executed overall | 34
| Number of defects encountered today | 9
| Number of defect encountered so far | 24
| Number of critical defects- still open | 19
Status for 03/23/2023
| Number of test cases planned | 37
| Number of test cases executed | 5
| Number of test cases executed overall | 39
| Number of defects encountered today | 5
| Number of defect encountered so far | 29
| Number of critical defects- still open | 24
Status for 03/24/2023
| Number of test cases planned | 38
| Number of test cases executed | 23
| Number of test cases executed overall | 62
| Number of defects encountered today | 7
| Number of defect encountered so far | 36
| Number of critical defects- still open | 31
Overall status
| Number of test cases planned | 150
| Number of test cases executed | 62
| Pass Percentage of the defects | 58.06%
| Defects density | 9 per day
| Critical defects percentage | 86.1%

## Detailed status
Module | Test Case | Scenario | Complexity | Responsible tester | Date of Execution(Can be past, present or future date) | Status(Pass/Fail/blocked/not executed) | Defect ID- Brief description | Severity | Status
USER LOGIN / LOGOUT
Travel | Log In | with correct credentials | medium | Sumeet | 2022-03-21 | Fail | 3: Does not ask for any user login credentials | 2- Medium | open
Travel | User Log In attemp | with incorrect password | medium | Sumeet | 2022-03-21 | Blocked | 4: Users can login without User Id, password | 2- Medium
Travel | User Log In attemp | User Log In with incorrect user Id | medium | Sumeet | 2022-03-21 | Blocked | 4: | 2- Medium
Travel | User Log In attemp | User Log In with incorrect user ID and password | medium | Sumeet | 2022-03-21 | Blocked | 4: | 2- Medium
Travel | User Log In attemp | User Log In with user ID field empty | medium | Sumeet | 2022-03-21 | Blocked | 4: | 2- Medium
Travel | User Log In attemp | User Log In with password field empty | medium | Sumeet | 2022-03-21 | Blocked | 4: | 2- Medium
Travel | User Log out | User Log Out | medium | Sumeet | 2022-03-21 | Blocked | 5: No log out button available for general user | 3- Low
ADMIN LOGIN / LOGOUT
Admin | admin Log In | with correct credentials | complex | Sumeet | 2022-03-22 | Fail | 6: Can not be submitted (Go button does not work) | 1- High | open
Admin | admin Log In attemp | with incorrect password | complex | Sumeet | 2022-03-22 | Not Executed |  | 1- High
Admin | admin Log In attemp | with incorrect user Id | complex | Sumeet | 2022-03-22 | Not Executed |  | 1- High
Admin | admin Log In attemp | with incorrect user ID and password | complex | Sumeet | 2022-03-22 | Not Executed |  | 1- High
Admin | admin Log In attemp | with user ID field empty | complex | Sumeet | 2022-03-22 | Not Executed |  | 1- High
Admin | admin Log In attemp | with password field empty | complex | Sumeet | 2022-03-22 | Not Executed |  | 1- High
Admin | admin Log out | Admin Log Out | complex | Sumeet | 2022-03-22 | Pass
USER REGISTRATION
Travel | Succesfull User Registration | with all valid credentials | complex | Sumeet | 2022-03-21 | Blocked | 1: User Registration page not available | 2- Medium
Travel | User Registration attemp | with lower boundary value for user Id | complex | Sumeet | 2022-03-21 | Blocked | 1: | 2- Medium
Travel | User Registration attemp | with upper boundary value for user Id | complex | Sumeet | 2022-03-21 | Blocked | 1: | 2- Medium
Travel | User Registration attemp | upper boundary value for password | complex | Sumeet | 2022-03-21 | Blocked | 1: | 2- Medium
Travel | User Registration attemp | with lower boundary value for password | complex | Sumeet | 2022-03-21 | Blocked | 1: | 2- Medium
Travel | User Registration attemp | with existing user Id and password (equivalent partion) | complex | Sumeet | 2022-03-21 | Blocked | 1: | 2- Medium
Travel | User Registration attemp | with existing email Id (equivalent partion) | complex | Sumeet | 2022-03-21 | Blocked | 1: | 2- Medium
Travel | User Registration attemp | with different email id (equivalent partion) | complex | Sumeet | 2022-03-21 | Blocked | 1: | 2- Medium
Travel | User Registration attemp | with existing Address (equivalent partion) | complex | Sumeet | 2022-03-21 | Blocked | 1: | 2- Medium
ADMIN REGISTRATION
Admin | Succesfull Admin Registration | with all valid credentials | complex | Sumeet | 2022-03-21 | Blocked | 2:Admin Registration page not available | 1- High
Admin | Admin Registration attemp | with lower boundary value for user Id | complex | Sumeet | 2022-03-21 | Blocked | 2: | 1- High
Admin | Admin Registration attemp | with upper boundary value for user Id | complex | Sumeet | 2022-03-21 | Blocked | 2: | 1- High
Admin | Admin Registration attemp | upper boundary value for password | complex | Sumeet | 2022-03-21 | Blocked | 2: | 1- High
Admin | Admin Registration attemp | with lower boundary value for password | complex | Sumeet | 2022-03-21 | Blocked | 2: | 1- High
Admin | Admin Registration attemp | with existing user Id and password (equivalent partion) | complex | Sumeet | 2022-03-21 | Blocked | 2: | 1- High
Admin | Admin Registration attemp | with existing email Id (equivalent partion) | complex | Sumeet | 2022-03-21 | Blocked | 2: | 1- High
Admin | Admin Registration attemp | with different email id (equivalent partion) | complex | Sumeet | 2022-03-21 | Blocked | 2: | 1- High
Admin | Admin Registration attemp | with existing Address (equivalent partion) | complex | Sumeet | 2022-03-21 | Blocked | 2: | 1- High
ADD NEW ROUTE
Route | Selecting Travel ID | Selecting the travel ID from the dropdown | complex | Libin | 21-03-2022 | Fail | No Travel ID selected from the dropdown(button doesn't work) | High | open
Route | Selecting Bus ID | Selecting the bus ID from the dropdown | complex | Libin | 21-03-2022 | Fail | No Bus ID selected from the dropdown(button doesn't work) | High | open
Route | Selecting Bus ID | Selecting/adding bus ID manually | complex | Libin | 21-03-2022 | Fail | No option to add bus ID manually | medium | open
Route | Selecting jouney date | Calendar feature doesn't work | complex | Libin | 21-03-2022 | Fail | No feature to select a date from calendar or to put date manually | High | open
Route | Inputting arrival time | invalid data | complex | Libin | 21-03-2022 | Fail | Takes any invalid time in the field. | High | open
Route | Inputting departure time | invalid data | complex | Libin | 21-03-2022 | Fail | Takes any invalid time in the field. | High | open
Route | Inputting the fare | invalid data | complex | Libin | 21-03-2022 | Fail | Takes any invalid time in the field. | High | open
Route | Submit buttin | With all possible inputs | complex | Libin | 21-03-2022 | Fail | Unable to submit as no options to select the jouney date | High | open
DELETE ROUTE
Route | Show details button | Selecting show details button | medium | Libin | 21-03-2022 | Fail | No access to the details of the selected route ID, that admin wishes to delete. | High | open
TESTIMONIAL
Testimonials | Give Testimonial with Valid Email | Valid Email Id is entered | Medium | Anugha | 2022-03-21 | Pass
Testimonials | Give Testimonial with Invalid Email | Invalid Email Id is entered | Medium | Anugha | 2022-03-21 | Fail | D_001 : Feedback is submitted for an Invalid Email Id. | 1- Medium | Open
Testimonials | Give Testimonial with Empty Email Field | Email field is left blank | Medium | Anugha | 2022-03-21 | Pass
Testimonials | Give Testimonial with Special Characters in Feedback | A Special Character is entered in Feedback | Medium | Anugha | 2022-03-21 | Pass
Testimonials | View Testimonial | View the entered testimonial on both sections of the page | Medium | Anugha | 2022-03-21 | Pass
Testimonials | User Asks to Give Feedback | User asks another user to provide the feedback | Medium | Anugha | 2022-03-21 | Pass
Testimonials | View Testimonial with Posted Date and Email Id | Give testimonial and view it to check whether it displays the posted date and email id | Medium | Anugha | 2022-03-21 | Pass
Testimonials | View Testimonial by Refreshing the Page | Give testimonial and refresh the page before viewing it in testimonials | Medium | Anugha | 2022-03-21 | Pass
Testimonials | Testimonial_Usability | Testing the factor of how easy it is to use the eWheelz application | Medium | Anugha | 2022-03-21 | Pass
ADMIN (ADD/DEL/VIEW USER)
Admin | Add user with valid UserID | Minimum valid characters are entered in the field of UserID | High | Stephy | 23-03-2022 | Blocked | 23: "Add User" option is not available. Can't add new user | High | Open
Admin | Add user with valid UserID | Maximum valid characters are entered in the field of UserID | High | Stephy | 23-03-2022 | Blocked | 23: "Add User" option is not available. Can't add new user | High | Open
Admin | Add user with Invalid UserID | (Min-1) characters are entered in the field of UserID | High | Stephy | 23-03-2022 | Blocked | 23: "Add User" option is not available. Can't add new user | High | Open
Admin | Add user with Invalid UserID | (Max+1) characters are entered in the field of UserID | High | Stephy | 23-03-2022 | Blocked | 23: "Add User" option is not available. Can't add new user | High | Open
Admin | Add user with Invalid UserID | Special characters are entered in the field of UserID | High | Stephy | 23-03-2022 | Blocked | 23: "Add User" option is not available. Can't add new user | High | Open
Admin | Add user with valid Password | Minimum valid characters are entered in the field of Password | High | Stephy | 23-03-2022 | Blocked | 23: "Add User" option is not available. Can't add new user | High | Open
Admin | Add user with valid Password | Maximum characters are entered in the field of Password | High | Stephy | 23-03-2022 | Blocked | 23: "Add User" option is not available. Can't add new user | High | Open
Admin | Add user with valid Password | Special characters are entered in the field of Password | High | Stephy | 23-03-2022 | Blocked | 23: "Add User" option is not available. Can't add new user | High | Open
Admin | Add user with Invalid Password | (Min-1) characters are entered in the field of Password | High | Stephy | 23-03-2022 | Blocked | 23: "Add User" option is not available. Can't add new user | High | Open
Admin | Add user with Invalid Password | (Max+1) characters are entered in the field of Password | High | Stephy | 23-03-2022 | Blocked | 23: "Add User" option is not available. Can't add new user | High | Open
Admin | Submit Button in Add User | Valid characters are entered in the field of UserID & Password, then click on Submit Button | High | Stephy | 23-03-2022 | Blocked | 23: "Add User" option is not available. Can't add new user | High | Open
Admin | Submit Button in Add User | Fields of UserID & Password are kept blank, then click on Submit Button | High | Stephy | 23-03-2022 | Blocked | 23: "Add User" option is not available. Can't add new user | High | Open
Admin | Reset Button in Add User | Valid characters are entered in the field of UserID & Password, then click on Reset Button to clear | High | Stephy | 23-03-2022 | Blocked | 23: "Add User" option is not available. Can't add new user | High | Open
Admin | Reset Button in Add User | Fields of UserID & Password are kept blank, then click on Reset Button to clear | High | Stephy | 23-03-2022 | Blocked | 23: "Add User" option is not available. Can't add new user | High | Open
Admin | View User | To view all the registered users or to view a particular user | High | Stephy | 23-03-2022 | Blocked | 24: "View User" option is not available. Can't view any user | High | Open
Admin | View and Delete User | To view the registered user and then click to delete that particular user | High | Stephy | 23-03-2022 | Blocked | 24: "View User" option is not available. Can't view any user 25: Delete user function is not available | High | Open
Admin | Delete user with valid UserID | Minimum valid characters are entered in the field of UserID | High | Stephy | 23-03-2022 | Blocked | 25: Delete user function is not available | High | Open
Admin | Delete user with valid UserID | Maximum valid characters are entered in the field of UserID | High | Stephy | 23-03-2022 | Blocked | 25: Delete user function is not available | High | Open
Admin | Delete user with Invalid UserID | (Min-1) characters are entered in the field of UserID | High | Stephy | 23-03-2022 | Blocked | 25: Delete user function is not available | High | Open
Admin | Delete user with Invalid UserID | (Max+1) characters are entered in the field of UserID | High | Stephy | 23-03-2022 | Blocked | 25: Delete user function is not available | High | Open
Admin | Delete user with Invalid UserID | Special characters are entered in the field of UserID | High | Stephy | 23-03-2022 | Blocked | 25: Delete user function is not available | High | Open
Admin | Change Password with valid UserID | Minimum valid characters are entered in the field of UserID | High | Stephy | 23-03-2022 | Blocked | 26: "Change password" function is not available | High | Open
Admin | Change Password with valid UserID | Maximum characters are entered in the field of UserID | High | Stephy | 23-03-2022 | Blocked | 26: "Change password" function is not available | High | Open
Admin | Change Password with Invalid UserID | (Min-1) characters are entered in the field of UserID | High | Stephy | 23-03-2022 | Blocked | 26: "Change password" function is not available | High | Open
Admin | Change Password with Invalid UserID | (Max+1) characters are entered in the field of UserID | High | Stephy | 23-03-2022 | Blocked | 26: "Change password" function is not available | High | Open
Admin | Change Password with Invalid UserID | Special characters are entered in the field of UserID | High | Stephy | 23-03-2022 | Blocked | 26: "Change password" function is not available | High | Open
Admin | Change Password with valid Old Password | Minimum valid characters are entered in the field of Old Password | High | Stephy | 23-03-2022 | Blocked | 26: "Change password" function is not available | High | Open
Admin | Change Password with valid Old Password | Maximum characters are entered in the field of Old Password | High | Stephy | 23-03-2022 | Blocked | 26: "Change password" function is not available | High | Open
Admin | Change Password with valid Old Password | Special characters are entered in the field of Old Password | High | Stephy | 23-03-2022 | Blocked | 26: "Change password" function is not available | High | Open
Admin | Change Password with Invalid Old Password | (Min-1) characters are entered in the field of Old Password | High | Stephy | 23-03-2022 | Blocked | 26: "Change password" function is not available | High | Open
Admin | Change Password with Invalid Old Password | (Max+1) characters are entered in the field of Old Password | High | Stephy | 23-03-2022 | Blocked | 26: "Change password" function is not available | High | Open
Admin | Change Password with valid New Password | Minimum valid characters are entered in the field of New Password | High | Stephy | 23-03-2022 | Blocked | 26: "Change password" function is not available | High | Open
Admin | Change Password with valid New Password | Maximum characters are entered in the field of New Password | High | Stephy | 23-03-2022 | Blocked | 26: "Change password" function is not available | High | Open
Admin | Change Password with valid New Password | Special characters are entered in the field of New Password | High | Stephy | 23-03-2022 | Blocked | 26: "Change password" function is not available | High | Open
Admin | Change Password with Invalid New Password | (Min-1) characters are entered in the field of New Password | High | Stephy | 23-03-2022 | Blocked | 26: "Change password" function is not available | High | Open
Admin | Change Password with Invalid New Password | (Max+1) characters are entered in the field of New Password | High | Stephy | 23-03-2022 | Blocked | 26: "Change password" function is not available | High | Open
Admin | Submit Button in Change Password option | Valid characters are entered in the field of UserID, Old Password & New Password, then click on Submit Button | High | Stephy | 23-03-2022 | Blocked | 26: "Change password" function is not available | High | Open
Admin | Submit Button in Change Password option | Fields of UserID, Old Password & New Password are kept blank, then click on Submit Button | High | Stephy | 23-03-2022 | Blocked | 26: "Change password" function is not available | High | Open
Admin | Reset Button in Change Password Option | Valid characters are entered in the field of UserID, Old Password & New Password, then click on Reset Button to clear | High | Stephy | 23-03-2022 | Blocked | 26: "Change password" function is not available | High | Open
Admin | Reset Button in Change Password Option | Fields of UserID, Old Password & New Password are kept blank, then click on Reset Button to clear | High | Stephy | 23-03-2022 | Blocked | 26: "Change password" function is not available | High | Open
ADD TRAVEL
Add Travel | Add Travel with no location selection | On skipping the location drop down | High | Akshara | 2022-03-22 | Fail | 1002 - Travel is added with a default location option. | High | Open
Add Travel | Add Travel with a Valid address | Valid address has MIN characters entered | Low | Akshara | 2022-03-22 | Pass |  | Low
Add Travel | Add Travel with a Valid address | Valid address has MAX characters entered | Low | Akshara | 2022-03-22 | Pass |  | Low
Add Travel | Add Travel with an invalid address | Address field is empty | High | Akshara | 2022-03-22 | Fail | 1003 - Travel is added even though the fields are empty | High | Open
Add Travel | Add Travels with an invalid address | Address field has special characters entered | High | Akshara | 2022-03-22 | Fail | 1004 - Travel is added with the address with special characters | High | Open
Add Travel | Add Travel with a Valid agent name | Valid agent name has MIN characters entered | Low | Akshara | 2022-03-22 | Pass |  | Low
Add Travel | Add Travel with a Valid agent name | Valid agent name has MAX characters entered | Low | Akshara | 2022-03-22 | Pass |  | Low
Add Travel | Add Travel with an invalid agent name | Agent name is empty | High | Akshara | 2022-03-22 | Fail | 1005 - Travel is added even though the fields are empty | High | Open
Add Travel | Add Travels with an invalid agent name | Agent name field has special characters entered | High | Akshara | 2022-03-22 | Fail | 1006 - Travel is added with the agent name with special characters | High | Open
Add Travel | Add Travels with a valid phone number | Valid phone number with 10 numeric characters | High | Akshara | 2022-03-22 | Pass |  | High
Add Travel | Add Travel with an invalid phone number | Phone number is empty | High | Akshara | 2022-03-22 | Fail | 1007 - Travel is added even though the fields are empty | High | Open
Add Travel | Add Travels with an invalid phone number | Phone number field has alpha numeric entered | High | Akshara | 2022-03-22 | Fail | 1008 - Travel is added with the phone number with alpha numeric characters | High | Open
Add Travel | Add Travels with an invalid phone number | Phone number field has special characters entered | High | Akshara | 2022-03-22 | Fail | 1009 - Travel is added with the phone number with special characters | High | Open
Add Travel | Submit button on the Add Travel page | The button is clickable | High | Akshara | 2022-03-22 | Pass |  | High
Add Travel | Clear button on the Add Travel page | The button is clickable | High | Akshara | 2022-03-22 | Pass |  | High
DELETE TRAVEL
Delete Travel | Select TravelsID from the drop down | Valid TravelsID is selected | High | Akshara | 2022-03-23 | Pass |  | High
Delete Travel | Select TravelsID from the drop down (on input) | Valid TravelsID can be inputted | Medium | Akshara | 2022-03-23 | Pass |  | Medium
Delete Travel | Delete Travel with no TravelsID selection | On skipping the drop down | High | Akshara | 2022-03-23 | Pass |  | High
Delete Travel | Delete button on the Delete Travel page | The button is clickable | High | Akshara | 2022-03-23 | Pass |  | High
Delete Travel | Show Details button on the Delete Travel page | The button is clickable | High | Akshara | 2022-03-23 | Fail | 1010 - The travel details are not visible, since the button does not function | High | Open
VIEW TRAVEL
View Travel | View Travel page displays data | List of all the agencies added are displayed in a table | High | Akshara | 2022-03-24 | Pass |  | High
View Travel | View button on the View Travel page | The button is clickable | High | Akshara | 2022-03-24 | Pass |  | High
View Travel | Add button on the View Travel page | The button is clickable | High | Akshara | 2022-03-24 | Pass |  | High
View Travel - ADD | Select BusType from the drop down | Valid BusType is selected | High | Akshara | 2022-03-24 | Pass |  | High
View Travel - ADD | Select BusType from the drop down (on input) | Valid BusType can be inputted | Medium | Akshara | 2022-03-24 | Pass |  | Medium
View Travel - ADD | Add Bus Details with no BusType selection | On skipping the drop down | High | Akshara | 2022-03-24 | Fail | 1011 - Bus details are added with a default option. | High | Open
View Travel - ADD | Add Bus Details with a Valid Bus number | Valid number has MIN characters entered | Low | Akshara | 2022-03-24 | Pass |  | Low
View Travel - ADD | Add Bus Details with a Valid Bus number | Valid number has MAX characters entered | Low | Akshara | 2022-03-24 | Pass |  | Low
View Travel - ADD | Add Bus Details with an invalid Bus number | Bus number field is empty | High | Akshara | 2022-03-24 | Fail | 1012 - Bus details are added even though the fields are empty | High | Open
View Travel - ADD | Add Bus Details with an invalid Bus number | Bus number field has special characters entered | High | Akshara | 2022-03-24 | Fail | 1013 - Bus details are added with the bus number with special characters | High | Open
View Travel - ADD | Add Bus Details with editing TravelsID ReadOnly field | ReadOnly field is not editable | High | Akshara | 2022-03-24 | Pass |  | High
View Travel - ADD | Submit button on the Add Bus Details page | The button is clickable | High | Akshara | 2022-03-24 | Pass |  | High
View Travel - ADD | Clear button on the Add Bus Details page | The button is clickable | High | Akshara | 2022-03-24 | Pass |  | High
RESERVATION MODULE: BOOK TICKET / CANCEL TICKET
Book Tickets | Navigate and click on "Book Tickets" page | "Book Ticket" button is present and clickable | High | Liceya | 2022-03-24 | Pass |  | High
Book Tickets | Selecting "from" location from dropdown | Click the dropdown and select a valid travel source location | Medium | Liceya | 2022-03-24 | Pass |  | Medium
Book Tickets | Selecting "To" location from dropdown | Click the dropdown and select a valid travel destination location | Medium | Liceya | 2022-03-24 | Pass |  | Medium
Book Tickets | Selecting the journey date | select a future available Date from the calander. Eg : "20-05-2022" | Medium | Liceya | 2022-03-24 | Fail | The Calander option is not working | High | Open
Book Tickets | Selecting an invalid travel date (Past Date) | Select a past Date from the calander. Eg : "20-01-2022" | Medium | Liceya | 2022-03-24 | Fail | The Calander option is not working | High | Open
Book Tickets | Selecting "Bus Type" from dropdown | Click the a bus type from the dropdown options. Eg : "Sleeper" | Medium | Liceya | 2022-03-24 | Pass |  | High
Book Tickets | Select a valid Number of passengers | Click on the text field for "Number of Passengers" and enter a valid number | Medium | Liceya | 2022-03-24 | Pass |  | High
Book Tickets | Select a in-valid Number of passengers (Beyond the capacity of the bus) | Click on the text field for "Number of Passengers" and enter a invalid number eg:300 | Medium | Liceya | 2022-03-24 | Fail | The Text field is taking entry beyond the capacity of the bus | High | Open
Book Tickets | Select a in-valid Number of passengers (any text value) | Click on the text field for "Number of Passengers" and enter a invalid text value. EG : ddaa | Medium | Liceya | 2022-03-24 | Fail | The text field is accepting any character value | High | Open
Book Tickets | Test the Check availability option | Clicking the option to view the available buses | Medium | Liceya | 2022-03-24 | Blocked | As the date is not selected we are not able to move further in the next page | High | Open
Book Tickets | Test the selction of bus | Select a bus from the available options | Medium | Liceya | 2022-03-24 | Blocked | As the date is not selected we are not able to move further in the next page | High | Open
Book Tickets | Click on "Proceed to Payment" | Click on "Proceed to Payment" to enter paymeent details and finally pay | High | Liceya | 2022-03-24 | Blocked | As the date is not selected we are not able to move further in the next page, We cannot select the bus or pay for booking | High | Open
Book Tickets | Test the "PaymentMode" dropdown | click on "PaymentMode" dropdown | High | Liceya | 2022-03-24 | Blocked | As the date is not selected we are not able to move further in the next page, We cannot select the bus or pay for booking | High | Open
Book Tickets | Test the "BankName" text field with valid Bank name | Click on the "BankName" Text field and enter the name | High | Liceya | 2022-03-24 | Blocked | As the date is not selected we are not able to move further in the next page, We cannot select the bus or pay for booking | High | Open
Book Tickets | Test the "BankName" text field with invalid Bank name | Click on the "BankName" Text field and enter any character or text value | High | Liceya | 2022-03-24 | Blocked | As the date is not selected we are not able to move further in the next page, We cannot select the bus or pay for booking | High | Open
Book Tickets | Test the "BankName" text field with Blank value | Click on the "BankName" Text field and enter space as value or do not enter any value | High | Liceya | 2022-03-24 | Blocked | As the date is not selected we are not able to move further in the next page, We cannot select the bus or pay for booking | High | Open
Book Tickets | Enter a valid Card number and test the "CardNo" text field | Click on the "CardNo" Text field and enter the number | High | Liceya | 2022-03-24 | Blocked | As the date is not selected we are not able to move further in the next page, We cannot select the bus or pay for booking | High | Open
Book Tickets | Enter an in-valid Card number and test the "CardNo" text field | Click on the "CardNo" Text field and enter any invalid number | High | Liceya | 2022-03-24 | Blocked | As the date is not selected we are not able to move further in the next page, We cannot select the bus or pay for booking | High | Open
Book Tickets | Enter an in-valid Card number and test the "CardNo" text field | Click on the "CardNo" Text field and enter any invalid characters | High | Liceya | 2022-03-24 | Blocked | As the date is not selected we are not able to move further in the next page, We cannot select the bus or pay for booking | High | Open
Book Tickets | leave the Card number empty | Click on the "CardNo" Text field and enter space or leave it empty | High | Liceya | 2022-03-24 | Blocked | As the date is not selected we are not able to move further in the next page, We cannot select the bus or pay for booking | High | Open
Book Tickets | Check the "NetAmount" Text field with valid input | click on "NetAmount" text field and Type the value. Eg: 200.00 | High | Liceya | 2022-03-24 | Blocked | As the date is not selected we are not able to move further in the next page, We cannot select the bus or pay for booking | High | Open
Book Tickets | Check the "NetAmount" Text field with invalid input | click on "NetAmount" text field and Type the invalid value. Eg: aada | High | Liceya | 2022-03-24 | Blocked | As the date is not selected we are not able to move further in the next page, We cannot select the bus or pay for booking | High | Open
Book Tickets | Check the "NetAmount" Text field with invalid input | click on "NetAmount" text field and Type the invalid value of numeric amount. Eg:20,000.00 | High | Liceya | 2022-03-24 | Blocked | As the date is not selected we are not able to move further in the next page, We cannot select the bus or pay for booking | High | Open
Book Tickets | Check the "NetAmount" Text field with null or blank value | click on "NetAmount" text field and leave it empty | High | Liceya | 2022-03-24 | Blocked | As the date is not selected we are not able to move further in the next page, We cannot select the bus or pay for booking | High | Open
Book Tickets | Check the "save" button | Click on "save" to save the details and move to next page | High | Liceya | 2022-03-24 | Blocked | As the date is not selected we are not able to move further in the next page, We cannot select the bus or pay for booking | High | Open
Cancel Ticket | Test the "Cancel Ticket" feature for valid ticket ID | Enter a valid Ticket ID and click "Cancel Ticket" | High | Liceya | 2022-03-24 | Blocked | As the date is not selected we are not able to move further in the next page, We cannot book a ticket. With no valid ticket id we cannot test the cancel option | High | Open
Cancel Ticket | Test the "Cancel Ticket" feature for invalid ticket ID | Enter an invalid Ticket ID and click "Cancel Ticket" | High | Liceya | 2022-03-24 | Pass |  | High

## Bug report
Defect ID | Test Script ID | Defect Description | Steps to reproduce | Severity | State | Created by | Assigned to
1 | TS_UREG_001 | User can not register | Navigate the eWheelz application Registration Page and find User Registration button/ link | 2- Medium | Open | Khaleda | Dev representative
Click on the "User Registration" option
User is at user registration page and enters all required information properly ASSUMPTION- username is unique in the system. Password must be a min of 6 characters, a mix of upper and lower case and include at least one special character such as $ username - min 6 max 10. (consider Equivalence partitioning and Boundary values).
Click on the "Submit" button or hit Enter Key
Expected Result: System will accept valid inputs and make user registration succesfully
Actual result: Registration page is not available
2 | TS_AREG_001 | Admin can not register | Navigate the eWheelz application Registration Page and find Admin Registration button/ link | 1- High | Open | Khaleda | Dev representative
Click on the "Admin Registration" option
Admin is at Admin registration page and enters all required information properly ASSUMPTION- Adminname is unique in the system. Password must be a min of 6 characters, a mix of upper and lower case and include at least one special character such as $ Adminname - min 6 max 10. (consider Equivalence partitioning and Boundary values).
Click on the "Submit" button or hit Enter Key
Expected Result: System will accept valid inputs and make Admin registration succesfully
Actual result: Registration page is not available
3 | TS_ULOG_001 | Does not ask for any user login credentials | Navigate the eWheelz application Home Page and find User Login button | 2- Medium | Open | Khaleda | Dev representative
Click on the "User Login" option in the homepage
The user enters the user Id and password. ASSUMPTION- User Id and password is already created throuh succesful user registration.(consider Equivalence partitioning).
Click on the "Submit" button or hit Enter Key
Expected result: User will provide ID password to login wit his own ceedentials
Actual result: User can login by clicking on USER Login button, without providing id pw information
4 | TS_ULOG_002 | Users can login without User Id, password | Navigate the eWheelz application Home Page and find User Login button | 2- Medium | Open | Khaleda | Dev representative
Click on the "User Login" option in the homepage
The user enters the user Id and password ASSUMPTION- password is incorrect/ does not match with corresponding user which is already created throuh user registration.(consider Equivalence partitioning).
Click on the "Submit" button or hit Enter Key
Expected result: User will provide ID password to login wit his own ceedentials
Actual result: User id pw fields are unavailable
5 | TS_ULOG_007 | Users have no log out button | Navigate the eWheelz application Home Page and find User Login button | 3- Low | Open | Khaleda | Dev representative
Click on the "User Login" option in the homepage
The user enters the user Id and password ASSUMPTION- password is incorrect/ does not match with corresponding user which is already created throuh user registration.(consider Equivalence partitioning).
Click on the "Submit" button or hit Enter Key
Expected result: User will see Log out button once login
Actual result: User can return by clicking on Home button, no log out button is available for general users
6 | TS_ALOG_001 | Admin Id Pw can not be submitted | Navigate the eWheelz application Home Page and find Admin Login button | 1- High | Open | Khaleda | Dev representative
Click on the "Admin Login" option in the homepage
The Admin enters the Admin Id and password. ASSUMPTION- Admin Id and password is already created throuh succesful Admin registration.(consider Equivalence partitioning).
Click on the "Submit" button or hit Enter Key
Expected result: Able to see and click on Submit button after entering admin ID Pw
Actual result: There is a Go button instead of submit, which does not work
7 | BTTC_004 | The Journey date option is not working | "1. Login to the site using the user credentials 2. Navigate to the Book Tickets button 3.Clicks on the date option 4. select a future date Expected result: It should display a calander option with past dates grayed out and future date available Actual Result: The calander is not appearing to select or view any dates" | High | Open | Liceya | Dev representative
8 | BTTS_005 | The Journey date option is not working, We cannot test the invalid date selection | 1. Login to the site using the user credentials 2. Navigate to the Book Tickets button 3.Clicks on the date option 4. select a past date Expected result: It should display a calander option with past dates grayed out and future date available. Actual Result: The calander is not appearing to select or view any dates | High | Open | Liceya | Dev representative
9 | BTTS_008 | "Number of Passangers" Text field is accepting invalid inputs. Numeric value is beyond the capacity of the bus | 1. Login to the site using the user credentials 2. Navigate to the Book Tickets button 3.Clicks on the "Number of passangers" text field 4. Type in a invalid number : 300 Expected result: It should display error message that please enter valid number of passangers. Actual Result: It is accepting the input. | High | Open | Liceya | Dev representative
10 | BTTS_009 | "Number of Passangers" Text field is accepting invalid inputs. It is accepting character input | 1. Login to the site using the user credentials 2. Navigate to the Book Tickets button 3.Clicks on the "Number of passangers" text field 4. Type in any character: aaaa Expected result: It should display error message that please enter valid number of passangers. Actual Result: It is accepting the input. | High | Open | Liceya | Dev representative
11 | BTTS_0010 | Once clicked on "Check Availabilty" button It should move to next page | 1. Login to the site using the user credentials 2. Navigate to the Book Tickets button 3.fill the form 4. Click on "Check Availabilty" button Expected result: It should move to the next page. Actual Result: It is not moving to next page. | High | Open | Liceya | Dev representative
12 | BTTS_0011 | click on "Proceed to payment" button to pay for the booking | 1. Login to the site using the user credentials 2. Navigate to the Book Tickets button 3.fill the form 4. Click on "Check Availabilty" button 5. Select a bus 6. Click on "Proceed to Payment" Expected result: It should move to the next page. Actual Result: It is not moving to next page. | High | Open | Liceya | Dev representative
13 | BTTS_0013 | User will not be able to view or select anything from "PaymentMode" Dropdown | 1. Login to the site using the user credentials 2. Navigate to the Book Tickets button 3.fill the form 4. Click on "Check Availabilty" button 5. Select a bus 6. Click on "Proceed to Payment" 7. Select a "PaymentMode" from dropdown Expected result: Payment form should be visible and editable. and user can select any payment method available Actual Result: The application does not move to the payment page. | High | Open | Liceya | Dev representative
14 | RMTC_012 | Travel Id can not be entered or validated | Navigate the eWheelz application admin Page and find Add route button | high | Open | Bhanu | Dev representative
User is at add route page and enters all required information properly
Admin will add all the data according to the inputs required.
ASSUMPTIONS: selecting travel id from the dropdown
Expected result: New route would be added in the database.
Actual result: java.sql.SQLException: Incorrect integer value: '' for column 'Travels ID' at row 1
15 | RMTC_013 | Bus Ids are not retrieved from database | Navigate the eWheelz application admin Page and find Add route button | high | Open | Bhanu | Dev representative
User is at add route page and enters all required information properly
Admin will add all the data according to the inputs required.
ASSUMPTIONS: selecting bus id from the dropdown
Expected result: New route would be added in the database.
Actual result: java.sql.SQLException: Incorrect integer value: '' for column 'Bus ID' at row 1
16 | RMTC_013 | Bus Id can not be entered manually | Navigate the eWheelz application admin Page and find Add route button | high | Open | Bhanu | Dev representative
User is at add route page and enters all required information properly
Admin will add all the data according to the inputs required.
ASSUMPTIONS: selecting bus id from the dropdown or inputting manually
Expected result: New route would be added in the database.
Actual result: java.sql.SQLException: Incorrect integer value: '' for column 'Bus ID' at row 1
17 | RMTC_014 | Journey Date field does not work or does not take any input date | Navigate the eWheelz application admin Page and find Add route button | high | Open | Bhanu | Dev representative
User is at add route page and enters all required information properly
Admin will add all the data according to the inputs required.
ASSUMPTIONS: selecting journey date from the calender
Expected result: New route would be added in the database.
Actual result: java.sql.SQLException: Incorrect integer value: '' for column 'Jouney date' at row 1
18 | RMTC_015 | Arrival* fields takes any invalid input | Navigate the eWheelz application admin Page and find Add route button | high | Open | Bhanu | Dev representative
User is at add route page and enters all required information properly
Admin will add all the data according to the inputs required.
ASSUMPTIONS: inputting any invalid arrival time
Expected result: New route should not be added in the database.
Actual result: java.sql.SQLException: Incorrect integer value: '' for column 'Jouney date' at row 1
19 | RMTC_017 | Fare* fields takes any invalid input | Navigate the eWheelz application admin Page and find Add route button | high | Open | Bhanu | Dev representative
User is at add route page and enters all required information properly
Admin will add all the data according to the inputs required.
ASSUMPTIONS: inputting any invalid fare
Expected result: New route should not be added in the database.
Actual result: java.sql.SQLException: Incorrect integer value: '' for column 'Jouney date' at row 1
20 | RMTC_015 | Departure* fields takes any invalid input | Navigate the eWheelz application admin Page and find Add route button | high | Open | Bhanu | Dev representative
User is at add route page and enters all required information properly
Admin will add all the data according to the inputs required.
ASSUMPTIONS: inputting any invalid departure time
Expected result: New route should not be added in the database.
Actual result: java.sql.SQLException: Incorrect integer value: '' for column 'Jouney date' at row 1
21 | RMTC_016 | Submit button does not work | Navigate the eWheelz application admin Page and find Add route button | high | Open | Bhanu | Dev representative
User is at add route page and enters all required information properly
Admin will add all the data according to the inputs required.
Expected result: New route should not be added in the database by hitting
Actual result: Submit button doesn't work.
22 | TS_002 | System accepts Invalid Email Id. | 1. Navigate to the Ewheelz application homepage. 2. Click on the "View Testimonial" option available on the left hand side of the screen. 3. Enter the "Your email Id" as "capstone". 4. Enter the "Feedback" as "eWheelz is amazing!!! I have used this website to book tickets several time :)". 5. Click on "Submit Feedback". Your Feedback submitted successfully! Expected result: Error Message showing "Your Feedback is not submitted as Invalid Email Id has been entered". Actual Result: Message showing "Your Feedback submitted successfully!. Thanks for providing your feedback". | 2- Medium | Open | Shikha | Dev Representative
23 | TS_001_AddUser TS_002_AddUser TS_003_AddUser TS_004_AddUser TS_005_AddUser TS_006_AddUser TS_007_AddUser TS_008_AddUser TS_009_AddUser TS_010_AddUser TS_011_AddUser TS_012_AddUser TS_013_AddUser TS_014_AddUser | "Add User" option is not available. Can't add new user | Navigate to the eWheelz application Admin login Page Enter the valid credentials to login and click "Submit" On the Admin page, click on "Add User" option Expected Result: A new window opens to Add User Actual Result: Add User option is not available | 1- High | Open | Puneet | Dev Representative
24 | TS_015_ViewUser | "View User" option is not available. Can't view any user | Navigate to the eWheelz application Admin login Page Enter the valid credentials to login and click "Submit" On the Admin page, click on "View User" option Expected Result: A new window opens to View all the User Actual Result: View User option is not available | 1- High | Open | Puneet | Dev Representative
25 | TS_016_DeleteUser TS_017_DeleteUser TS_018_DeleteUser TS_019_DeleteUser TS_020_DeleteUser TS_021_DeleteUser | "Delete User" option is not available. Can't delete any user | Navigate to the eWheelz application Admin login Page Enter the valid credentials to login and click "Submit" On the Admin page, click on "Delete User" option Expected Result: A new window opens to Delete the User Actual Result: Delete User option is not available | 1- High | Open | Puneet | Dev Representative
26 | TS_022_ChangePswd TS_023_ChangePswd TS_024_ChangePswd TS_025_ChangePswd TS_026_ChangePswd TS_027_ChangePswd TS_028_ChangePswd TS_029_ChangePswd TS_030_ChangePswd TS_031_ChangePswd TS_032_ChangePswd TS_033_ChangePswd TS_034_ChangePswd TS_035_ChangePswd TS_036_ChangePswd TS_037_ChangePswd TS_038_ChangePswd TS_039_ChangePswd TS_040_ChangePswd | "Change Password" option is not available. Can't change password for any user | Navigate to the eWheelz application Admin login Page Enter the valid credentials to login and click "Submit" On the Admin page, click on "Change Password" option Expected Result: A new window opens to Change the User's Password Actual Result: Change Password option is not available | 1- High | Open | Puneet | Dev Representative
27 | TC_ADD_005 | Travel is added even though the Travel name field is empty | 1. Login to the site using the admin credentials 2. Navigate to the Add Travel button 3. Leave the name field empty with all the other valid data 4. Activate the submit button Expected result: It should display an error and not submit since it is a mandatory field Actual Result: It submits the data with an empty name | High | Open | Akshara | Dev representative
28 | TC_ADD_006 | Travel is added with the name with special characters | 1. Login to the site using the admin credentials 2. Navigate to the Add Travel button 3. Enter special characters in the name field with all the other valid data 4. Activate the submit button Expected result: It should display an error and not submit since it contains invalid name and values Actual Result: It submits the data with all the special characters | High | Open | Akshara | Dev representative
29 | TC_ADD_009 | Travel is added with a default location option. | 1. Login to the site using the admin credentials 2. Navigate to the Add Travel button 3. Skip selecting any option for location 4. Activate the submit button Expected result: It should display an error and not submit since no options were selected Actual Result: It submits the data with a default location without alerting the user about it. | High | Open | Akshara | Dev representative
30 | TC_ADD_014 | Travel is added even though the Travel address field is empty | 1. Login to the site using the admin credentials 2. Navigate to the Add Travel button 3. Leave the address field empty with all the other valid data 4. Activate the submit button Expected result: It should display an error and not submit since it is a mandatory field Actual Result: It submits the data with an empty address | High | Open | Akshara | Dev representative
31 | TC_ADD_015 | Travel is added with the address with special characters | 1. Login to the site using the admin credentials 2. Navigate to the Add Travel button 3. Enter special characters in the address field with all the other valid data 4. Activate the submit button Expected result: It should display an error and not submit since it contains invalid name and values Actual Result: It submits the data with all the special characters | High | Open | Akshara | Dev representative
32 | TC_ADD_020 | Travel is added even though the Travel address field is empty | 1. Login to the site using the admin credentials 2. Navigate to the Add Travel button 3. Leave the agent name field empty with all the other valid data 4. Activate the submit button Expected result: It should display an error and not submit since it is a mandatory field Actual Result: It submits the data with an empty agent name | High | Open | Akshara | Dev representative
33 | TC_ADD_021 | Travel is added with the address with special characters | 1. Login to the site using the admin credentials 2. Navigate to the Add Travel button 3. Enter special characters in the agent name field with all the other valid data 4. Activate the submit button Expected result: It should display an error and not submit since it contains invalid name and values Actual Result: It submits the data with all the special characters | High | Open | Akshara | Dev representative
34 | TC_ADD_025 | Travel is added even though the Travel address field is empty | 1. Login to the site using the admin credentials 2. Navigate to the Add Travel button 3. Leave the agent name field empty with all the other valid data 4. Activate the submit button Expected result: It should display an error and not submit since it is a mandatory field Actual Result: It submits the data with an empty agent name | High | Open | Akshara | Dev representative
35 | TC_ADD_026 | Travel is added with the address with alpha numeric characters | 1. Login to the site using the admin credentials 2. Navigate to the Add Travel button 3. Enter alpha numeric characters in the phone number field with all the other valid data 4. Activate the submit button Expected result: It should display an error and not submit since it contains invalid name and values Actual Result: It submits the data with all the alpha numeric characters | High | Open | Akshara | Dev representative
36 | TC_ADD_027 | Travel is added with the address with special characters | 1. Login to the site using the admin credentials 2. Navigate to the Add Travel button 3. Enter special characters in the agent name field with all the other valid data 4. Activate the submit button Expected result: It should display an error and not submit since it contains invalid name and values Actual Result: It submits the data with all the special characters | High | Open | Akshara | Dev representative
37 | TC_DEL_007 | 1010 - The travel details are not visible, since the button does not function | 1. Login to the site using the admin credentials 2. Navigate to the Delete Travel button 3. Select a TravelsID from the dropdown 4. Activate the Show details button Expected result: It should display details of the selected option. Actual Result: The button does not function and fails to display he corresponding details of the option selected. | High | Open | Akshara | Dev representative
38 | TC_VIEW_008 | Bus details are added with a default option. | 1. Login to the site using the admin credentials 2. Navigate to the View Travel button and activate it 3. Select the add button of any of the TravelsID 4. Skip selecting any option for the bustype 4. Activate the submit button Expected result: It should display an error and not submit since no options were selected Actual Result: It submits the data with a default option without alerting the user about it. | High | Open | Akshara | Dev representative
39 | TC_VIEW_013 | Bus details are added even though the fields are empty | 1. Login to the site using the admin credentials 2. Navigate to the View Travel button and activate it 3. Select the add button of any of the TravelsID 4. Leave the bus details field empty with all the other valid data 5. Activate the submit button Expected result: It should display an error and not submit since it is a mandatory field Actual Result: It submits the data with an empty bus number | High | Open | Akshara | Dev representative
40 | TC_VIEW_014 | Bus details are added with the bus number with special characters | 1. Login to the site using the admin credentials 2. Navigate to the View Travel button and activate it 3. Select the add button of any of the TravelsID 4. Enter special characters in the bus number field with all the other valid data 4. Activate the submit button Expected result: It should display an error and not submit since it contains invalid name and values Actual Result: It submits the data with the bus number | High | Open | Akshara | Dev representative
41 | BTTS_0014 | User will not be able to Type a valid Bank name in the "BankName" text field | 1. Login to the site using the user credentials 2. Navigate to the Book Tickets button 3.fill the form 4. Click on "Check Availabilty" button 5. Select a bus 6. Click on "Proceed to Payment" 7. Type in a valid input in the "BankName" field Expected result: Payment form should be visible and editable. User can type in a valid bank name Actual Result: The application does not move to the payment page. | High | Open | Liceya | Dev representative
42 | BTTS_0015 | User will not be able to Type an invalid Bank name in the "BankName" text field. We cannot text if the application is taking invalid bank name | 1. Login to the site using the user credentials 2. Navigate to the Book Tickets button 3.fill the form 4. Click on "Check Availabilty" button 5. Select a bus 6. Click on "Proceed to Payment" 7. Type in a invalid input in the "BankName" field Expected result: Payment form should be visible and editable. User enters an invalid data in the field and the system should throw error Actual Result: The application does not move to the payment page. | High | Open | Liceya | Dev representative
43 | BTTS_0016 | We cannot test if the "BankName" field is considered as mandatory field by the application or not | 1. Login to the site using the user credentials 2. Navigate to the Book Tickets button 3.fill the form 4. Click on "Check Availabilty" button 5. Select a bus 6. Click on "Proceed to Payment" 7. leave the "BankName" blank Expected result: Payment form should be visible and editable. Actual Result: The application does not move to the payment page. | High | Open | Liceya | Dev representative
44 | BTTS_0017 | We cannot test the "CardNo" text field | 1. Login to the site using the user credentials 2. Navigate to the Book Tickets button 3.fill the form 4. Click on "Check Availabilty" button 5. Select a bus 6. Click on "Proceed to Payment" 7. enter a valid "CardNo" Expected result: Payment form should be visible and editable. Application should verify the "CardNo" and accept if it is valid Actual Result: The application does not move to the payment page. | High | Open | Liceya | Dev representative
45 | BTTS_0018 | We cannot test the "CardNo" text field with invalid | 1. Login to the site using the user credentials 2. Navigate to the Book Tickets button 3.fill the form 4. Click on "Check Availabilty" button 5. Select a bus 6. Click on "Proceed to Payment" 7. enter a valid "CardNo" Expected result: Payment form should be visible and editable. Application should verify the "CardNo" and throw error if it is not valid Actual Result: The application does not move to the payment page. | High | Open | Liceya | Dev representative
46 | BTTS_0019 | We cannot test the "CardNo" text field with invalid | 1. Login to the site using the user credentials 2. Navigate to the Book Tickets button 3.fill the form 4. Click on "Check Availabilty" button 5. Select a bus 6. Click on "Proceed to Payment" 7. enter a valid "CardNo" Expected result: Payment form should be visible and editable. Application should verify the "CardNo" and throw error if it is not valid Actual Result: The application does not move to the payment page. | High | Open | Liceya | Dev representative
47 | BTTS_0020 | We cannot test the "CardNo" text field with invalid | 1. Login to the site using the user credentials 2. Navigate to the Book Tickets button 3.fill the form 4. Click on "Check Availabilty" button 5. Select a bus 6. Click on "Proceed to Payment" 7. Leave the "CardNo" blank Expected result: Payment form should be visible and editable. Application should verify the "CardNo" and throw error if it is not valid. If no number entered the aplication should ask the user to enter the number. Actual Result: The application does not move to the payment page. | High | Open | Liceya | Dev representative
48 | BTTS_0021 | The field "NetAmount" can not be tested | 1. Login to the site using the user credentials 2. Navigate to the Book Tickets button 3.fill the form 4. Click on "Check Availabilty" button 5. Select a bus 6. Click on "Proceed to Payment" 7.enter a valid ammount in the "NetAmount" text feild Expected result: Payment form should be visible and editable. Application should verify the "NetAmount" and accept the input. Actual Result: The application does not move to the payment page. | High | Open | Liceya | Dev representative
49 | BTTS_0022 | The field "NetAmount" can not be tested | 1. Login to the site using the user credentials 2. Navigate to the Book Tickets button 3.fill the form 4. Click on "Check Availabilty" button 5. Select a bus 6. Click on "Proceed to Payment" 7. Enter invalid input Expected result: Payment form should be visible and editable. Application should verify the "NetAmount" and throw error if it is not valid. If no number entered the aplication should ask the user to enter the number. Actual Result: The application does not move to the payment page. | High | Open | Liceya | Dev representative
50 | BTTS_0023 | The field "NetAmount" can not be tested | 1. Login to the site using the user credentials 2. Navigate to the Book Tickets button 3.fill the form 4. Click on "Check Availabilty" button 5. Select a bus 6. Click on "Proceed to Payment" 7. Enter invalid input Expected result: Payment form should be visible and editable. Application should verify the "NetAmount" and throw error if it is not valid. If no number entered the aplication should ask the user to enter the number. Actual Result: The application does not move to the payment page. | High | Open | Liceya | Dev representative
51 | BTTS_0024 | The field "NetAmount" can not be tested | 1. Login to the site using the user credentials 2. Navigate to the Book Tickets button 3.fill the form 4. Click on "Check Availabilty" button 5. Select a bus 6. Click on "Proceed to Payment" 7. Leave the "NetAmount" blank Expected result: Payment form should be visible and editable. Application should verify the "NetAmount" and throw error if it is not valid. If no number entered the aplication should ask the user to enter the number. Actual Result: The application does not move to the payment page. | High | Open | Liceya | Dev representative
52 | BTTS_0025 | The "Save" option cannot be tested | 1. Login to the site using the user credentials 2. Navigate to the Book Tickets button 3.fill the form 4. Click on "Check Availabilty" button 5. Select a bus 6. Click on "Proceed to Payment" 7. fill the details in payment form 8. Click save Expected result: Payment form should be visible and editable. Application should allow the details to be saved. if all the datas are correct. Actual Result: The application does not move to the payment page. | High | Open | Liceya | Dev representative
53 | CTTS_001 | We cannot test the cancel ticket feature | 1. Login to the site using the user credentials 2. Navigate to the Cancel tickets button 3.fill the form with valid Ticket ID 4. select Cancel Expected result: Application varifyies the ticket id and cancel it Actual Result: The application does not have any ticket created we cannot check the functionality | High | Open | Liceya | Dev representative
54
55
56
57
58
59